## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Dnyaneshwar Khune | 2025-12-08 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2025-12-09 | Closed | Issue resolved and validated with sample programs
2 | Dnyaneshwar Khune | 2025-12-09 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2025-12-11 | Closed | Style detection accuracy improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others